## Slide 1
FinFlow
Family Finance OS
v7 Roadmap
CEO Sequencing · Honest Trade-offs · 14-Week Sprint Plan
From v6 React stack to a production-ready v7. Three features ship in v7. Two ship in v7.5. Two require a real backend and ship in v8 with cloud foundation. This deck is the operating sequence — not the wish list.
WHAT'S INSIDE
01 Codebase Reality Check
02 Sequencing · 3 Tiers
03 Smart Onboarding
04 EMI Re-amortisation
05 Recurring + Reminders
06 AI Planner (rules-based)
07 AI Chatbot (v7.5)
08 Admin Backend (v8)
09 Analytics & NorthStar
10 14-Week Sprint Plan
11 What's NOT in v7
12 CEO Decision Points
v7 PRD · 2025 · Confidential

## Slide 2
§01 · CODEBASE REALITY CHECK
Where the product actually is.
v6 is a feature-rich personal finance manager. The strategic plan said 'household OS with employer channel.' The two are not the same.
WHAT IS BUILT (v6.0)
9-page personal finance manager
Multi-profile workspace
Debts + Net Worth + Multi-currency
EMI calculator (basic)
Family Pulse Score (5 components)
React + TS + Tailwind + Recharts
DataAdapter abstraction (cloud-ready)
Local storage only · single-device
WHAT IS NOT BUILT
Open Banking integration (the thesis)
Employer channel / B2B portal
Real backend / multi-tenancy / auth
Accountability circles · peer matching
Pulse Score B2B licensing API
Multi-device sync · cloud
Real users · only test data
School channel · institutional moat
The strategic question this PRD does not solve: v7 polishes what we built. It does not move us closer to the household OS thesis. That is v8 (Open Banking) + v9 (multi-tenancy + employer channel). Decide consciously before v7 ships.
2 / 12

## Slide 3
§02 · SEQUENCING
Three tiers. Honest pacing.
Seven proposed features. Three ship in v7. Two in v7.5. Two require cloud and ship in v8.
TIER 1 · v7
14 weeks · Q1
Ship now
1
Smart Onboarding · Profile Templates
Pure frontend. Highest leverage.
2
EMI Re-amortisation Logic
Quality bar fix on existing feature.
3
Recurring + Notifications + Reminders
Three features collapse to one.
TIER 2 · v7.5
+8 weeks · Q2
Ship after backend MVP
4
AI Planner (rules-based)
Deterministic. No hallucination risk.
5
AI Chatbot (Q&A on data)
Needs Supabase Edge Function.
TIER 3 · v8 / v9
+6+ months
Need cloud foundation first
6
Admin Backend (separate app)
Needs real users in cloud DB.
7
Product Analytics + KPIs
Lives inside admin app.
Total v7 scope: 14 weeks · 2 frontend engineers · 1 designer · 0.5 backend (service worker)
3 / 12

## Slide 4
§03 · V7 FEATURE 1 · SMART ONBOARDING
From blank slate to right-fit in 90 seconds.
💑
Young Couple
Pre-populated:
Splits + Joint goals + Rent budgets
👨‍👩‍👧
Family with Kids
Pre-populated:
Members + Mortgage + School fees
💪
Single / Single Parent
Pre-populated:
Emergency fund + Benefits checker
💼
Self-Employed / SMB
Pre-populated:
P/B firewall + GST + Tax goal
🌅
Pre-Retiree / Retiree
Pre-populated:
Drawdown + Healthcare + Pension
🎓
Student / Early Career
Pre-populated:
Student loan + Course budgets
4-STEP FLOW
Q1: Which describes you? → Q2: Household size? → Q3: Primary concern? → Q4: Currency + language · Target: 90 seconds median
4 / 12

## Slide 5
§04 · V7 FEATURE 2 · EMI RE-AMORTISATION
Fix the math. Then give users a real choice.
THE PROBLEM TODAY
£200K mortgage · 5% APR · 25-year tenure · £1,170 EMI
Month 1: £833 interest, £337 principal · Month 120: £625 interest, £545 principal · Month 300: £5 interest, £1,165 principal. Current EMI tracker shows a flat split.
WHEN A USER MAKES A PART-PAYMENT, GIVE THEM THIS CHOICE:
Option A · Default
Reduce Tenure
EMI stays £1,170. Loan ends earlier. Saves the most interest. (Most common in India.)
Option B
Reduce EMI
Tenure stays 25 years. Monthly EMI drops to £1,032. Better cash flow today.
Option C
Apply as Advance
Both unchanged. Next 4 EMIs auto-marked paid. No schedule disruption.
Refactor: src/lib/calculations.ts · Match Bank of England PMT calculator within £0.01 · Validate against 5 real loan statements
5 / 12

## Slide 6
§05 · V7 FEATURE 3 · RECURRING + REMINDERS
Two features that don't ship apart.
Recurring without reminders is half a feature. Reminders without recurring has nothing to remind.
PART A · RECURRING SCHEDULE ENGINE
Schedule object
weekly | monthly | yearly | custom day-of-month
Auto-generation
Creates pending transaction at scheduled time
Confirmation flow
User confirms or auto-confirms (toggle)
New 'Recurring' page
All schedules · next due · status · running total
PART B · NOTIFICATIONS SYSTEM
Upcoming bill
3 days before · default ON · per-bill toggle
Missed payment
Day after · default ON · critical
Budget threshold
80% / 100% category · default OFF · opt-in
Goal milestone
25% / 50% / 75% / 100% · default ON
Custom reminder
User-defined date + message · manual
DELIVERY:
In-app center · Web Push API · PWA notifications · NOT in v7: SMS, email, native push (those need backend + native app)
6 / 12

## Slide 7
§06 · V7.5 · AI PLANNER
Rules-based first. LLM second.
WHY v7.5 IS RULES-BASED — NOT LLM
LLM-driven financial advice = regulatory landmine. We're not FCA-authorised. Suggesting investment moves to users via an LLM exposes us to advice liability and hallucination risk on someone's actual money. v7.5 ships a deterministic rules engine. The LLM upgrade is v8 with proper disclaimers and guardrails.
FIVE-DOMAIN ANALYSIS · DETERMINISTIC · ZERO HALLUCINATION
Income
Stability score · diversification
"Single source of income. 6-month emergency fund recommended."
Expenses
% of income · top categories · trends
"You spend 78% of income — 8% above healthy threshold."
Investments
% invested · allocation · liquidity
"You invest 4%. Age-band target: 15%. Consider SIPP/Roth."
Debt
DTI ratio · APR-weighted avg · payoff
"DTI 38%. Healthy: 36%. Avalanche credit card before 401k."
Tax
ISA/SIPP gaps · region-specific
"You've used £3,200 of £20,000 ISA allowance."
Engine: src/lib/plannerRules.ts · ~30 rules covering 90% of household scenarios · Each rule = priority + severity + trigger function
7 / 12

## Slide 8
§07 · V7.5 · AI CHATBOT
Why this needs a backend.
ARCHITECTURE · WHY IT SHIPS WITH v7.5 · NOT v7
1
Browser
User question typed
2
Edge Function
Auth check · summarise data · privacy filter
3
Claude API
Receives summary + question · returns answer
4
User UI
Streamed response in chat panel
WHAT IT CAN DO
How much did I spend on groceries last month?
Am I on track for my emergency fund goal?
Why did my Pulse Score drop this month?
Show me a summary of December.
WHAT IT CANNOT DO
Recommend specific stocks or investment products
File taxes or transfer money
Read individual transaction descriptions (privacy)
Answer outside the user's own data scope
Engine: Supabase Edge Function · Claude Haiku 4.5 · Privacy: aggregates only — never raw transactions or merchant names
8 / 12

## Slide 9
§08 · V8 · ADMIN BACKEND
Why this is v8, not v7.
BUILDING THIS NOW = WASTE
Admin backend has nothing to administer until users exist in a real database. v6 = localStorage. There are no centralised users. The admin app would query nothing. v8 ships Supabase auth + multi-tenancy. THEN admin makes sense. Building against fake data wastes 6 weeks of frontend capacity.
THREE ROLE TIERS · WHEN IT SHIPS IN v8
Super Admin
Everything
Founders + CTO
User mgmt · Content · Billing · Audit · Settings
Roles Admin
Users only
Customer Success lead
Create/edit/delete users · Reset passwords · Refunds
Content Admin
Articles only
Marketing / Editor
Article CRUD · Publish workflow · Tagging
Why a SEPARATE app: different bundle (consumers don't ship admin code) · different auth (admin SSO) · different deploy cadence · different security posture (VPN/IP allowlist)
9 / 12

## Slide 10
§09 · V8 · PRODUCT ANALYTICS & NORTHSTAR
What we measure when there is something to measure.
NORTHSTAR METRIC
Active Households per Week (AHpW)
An active household has 2+ members logged in or recording transactions in past 7 days. Single-user accounts count as 0.5. Captures the thesis: FinFlow only works if the household, not the individual, adopts it.
KPIs PER MODULE · MEASURED IN v8 ADMIN APP
ONBOARDING
Time to first transaction
< 90s
ACTIVATION
D7 retention
> 60%
HOUSEHOLD
% with 2+ active members
> 40%
RETENTION
D90 retention
> 50%
PULSE SCORE
% improving in 30 days
> 70%
REMINDERS
% triggering payment
> 80%
AI PLANNER
% recs followed in 14d
> 25%
REVENUE
Free → paid in 30 days
> 8%
Stack: PostHog · Stripe · Intercom · Sentry · in-app NPS at D30/D90/D365
10 / 12

## Slide 11
§10 · V7 SPRINT PLAN
14 weeks. 7 sprints. Honest pacing.
S1
Wk 1–2
Onboarding · Engine
Template definitions · Profile.template field · Migration for existing v6 users
S2
Wk 3–4
Onboarding · Polish
UI polish · Pre-population logic · Settings hook · Help section update
S3
Wk 5–6
EMI · Refactor
calculateAmortizationSchedule · Audit math against BoE PMT · 5 real-loan validation
S4
Wk 7–8
EMI · Part-Payment
Three-option modal · Re-amortisation engine · Interest history chart
S5
Wk 9–10
Recurring · Engine
Schedule object · Background generator · Pending confirmation flow · Recurring page
S6
Wk 11–12
Notifications
Center component · Settings panel · Web Push · Service worker · 6 notification types
S7
Wk 13–14
Hardening
QA · Regression on v6 · Beta release to 50 users · p0 bug fixes · v7 tag
Resourcing: 2 frontend engineers · 1 designer · 0.5 backend (service worker only) · QA continuous
11 / 12

## Slide 12
§11 · CEO DECISION POINTS
What I need you to decide.
01
Does v7 ship in 14 weeks with these 3 features only?
RECOMMENDED. Discipline is what makes v7 ship. Adding feature 4 makes v7 a 22-week project that ships nothing well.
02
Is the v8 thesis the household OS — or the feature-rich consumer app?
Open Banking + employer channel were the original thesis. They are not in this roadmap. Reconsider before v7 ends.
03
Do we accept that AI Planner is rules-based until v8?
RECOMMENDED. LLM advice without FCA authorisation is real legal risk. Rules-based is enough.
04
Is the admin app worth waiting for v8 backend, or do we hack a localStorage admin?
WAIT. Admin app on localStorage is a 6-week distraction with zero strategic value.
05
What is our position on 'we built a finance app' vs 'we are building the household OS we sold'?
OPEN QUESTION. The codebase has drifted from the strategic plan. Decide before v7 ships, not after.
FinFlow · v7 Roadmap · CEO-sequenced · Confidential · 2025